## Sheet1
Cosy Pets Project Gantt Chart
2026-01-19
Task No. | Sub Task | Task Description | Time: | Design Stage |  |  |  | Development Stage |  |  |  |  | Review
1 | 1.1 | Research Interfaces | 1 day | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 |  | Week 7 | Week 8 | Week 9
2 | 1.2 | Put in place meetings with the client for the project requirements | 3 days
3 | 1.3 | Project Propersal | 5 days
|  | Design | 15 days
4 | 1.1 | Design- Home Screen, information about Cosy Pets & Facilities provided | 4 days
4 | 1.2 | Design- Attraction screens | 3 days
3 | 1.3 | Design- Get user feedback,improving our community | 2 days
1 | 1.3 | Design- Pre-order screen, can select which of the following facilities they want for their pet | 3 days
5 | 1.2 | Confirmation with my client- Admiring the initial design or to make any necessary changes | 3 days
|  | Prototype | 35 days
6 | 1.1 | Testing- Facilities provided and information about the enviroment your pet will be in | 4 days
6 | 1.3 | Prototype- Facilities provided and information about the enviroment your pet will be in | 2 days
5 | 1.2 | Testing- Pre-order screen, can select which nutrients in food they need so emergencies are prevented | 4 days
6 | 1.2 | Prototype- Pre-order screen, can select which nutrients in food they need so emergencies are prevented | 4 days
7 | 1.3 | Testing- Facilities screens, what facilities are available for your pet | 2 days
5 | 1.1 | Prototype-Facilities screens, what facilities are available for your pet | 5 days
7 | 1.1 | Testing- User feedback, to improve or make any changes to our interface | 5 days
7 | 1.3 | Prototype- User feedback, to improve or make any changes to our interface | 4 days
6 | 1.2 | Testing- Whole interface, making sure it works with no faults occuring | 5 days
|  | Implementation | 15 days
8 | 1.3 | Implementation- Configureation Principles | 3 days
8 | 1.1 | Implementation- User- Friendly (ease of use) | 4 days
9 | 1.1 | Implementation- Accessibility Features | 2 days
8 | 1.2 | Implementation- User Needs (user requirements) | 1 day
9 | 1.3 | Meeting with my client- Finalization of the entire interface | 5 days | [6 empty] | oooi
|  | Review | 8 days
10 | 1.2 | Review- Home Screen | 2 days
10 | 1.2 | Review- Pets information screen | 1 day
10 | 1.1 | Review- Pet facility screen | 1 day
10 | 1.3 | Review- Pre-Purchase screen | 1 day
11 | 1.1 | Review- Total interface | 1 day
11 | 1.2 | Review- Final meeting with my client- Successfully passing on my interface | 2 days
Key Milestones:
Key milestones are visual representations, often using a solid dark shape to symbolise it within a project timescale, that highlights a significant point of victor, achievement or a major turning point in progress and dedication to my interface.
A primary example of these important ponts is holding regular project metings. These meeting will help undertake future mistakes and errors so that the interface will be at the best of their levels. Also it can prevent the needs to revisit the interface so that it could reproachfully impact future tasks.
Task Dependancies: The core idea behind this is that I have to ensure that previous tasks are done before I move on to the next stage. Also, a specific assignment is well crucial because several upcoming tasks rely entirely on it's successful performance.
A key example is the closing meeting with the client before putting forward my interface, ensuring that the initial work is of a high standard before proceeding to the next phase.
Last but not least, the client will examine the entire interface including the customer needs and all the implementation systems that will act like a helpline to our customers, so I willl have to be satisfied before having the last and final meeting with my client.
Task Dependacies:
I must ensure to fully complete the current task with significant skill before moving onto the next stage of the interface.
A primary example of this concept is the last client meeting where the interface is passed on. Before that meeting with my client, all pages must be carefully reviewed and with the client's specifications, preventing future corrections or adjustments to achieve the most successful and possible interface.